## Sheet1
week 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | week14
|  |  | Lit review: Compare and contrast network types/ hardware types, Investigate tradeoff of # components trained on, misc neuromorphic implementation | [9 empty] | Done
Implement CNN in Python
Basic matrix multiplication architecture
Train Model and save weights
Hspice Sim
Have something
Weight implementation
FPGA Dev
have something
Final Report/Presentation
Simulate ddc with SoC/FPGA

## Sheet2
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Date | 2021-01-21 | 2021-01-28 | 2021-02-04 | 2021-02-11 | 2021-02-18 | 2021-02-25 | 2021-03-04 | 2021-03-11 | 2021-03-18 | 2021-03-25 | 2021-04-01 | 2021-04-08 | 2021-04-15 | 2021-04-22 | 2021-04-27
Lit review: Compare and contrast network architectures/hardware implementations, Investigate tradeoff of # components network is trained on, neuromorphic architecture implementation
Implement CNN in Python
Devise matrix multiplication architecture for processor
Train model and save weights
Determine best weight implementation
HSPICE simulation development
FPGA Developmemt
Simulate SDR circuit with SoC/FPGA
Final Report/Presentation
Key
Corey's Tasks
Josh's Tasks
Both